## Sheet1
Requirment ID | As a | I should be able to | Sprint # | Comments | Marks
1 | Tourist/ Advertiser/ Tour Guide/ Seller/ Tourism Governor/Admin | Login using username and password | 1 |  | 6
2 | Tourist/ Tour Guide/ Advertiser/ Tourism Governor/ Admin/ Seller | Change my password | 1 |  | 6
3 | Tourist/ Tour Guide/ Advertiser/ Tourism Governor/ Admin/ Seller | Forget my password using an OTP sent to my email | 1 |  | 6
4 | Guest | Register (sign up) as a tourist using email, username, password, mobile number, nationality, DOB, job/student | 1 | DOB cannot be changed. Anyone under the age of 18 cannot book anything on the website. | 2
5 | Guest | Register (sign up) as a tour guide/ advertiser/ seller on the system with username, email and password | 1 |  | 3
6 | Guest | Upload required documents | 1 | ID and certificates for tour guide, ID and taxation registery card for advertisers, ID and taxation registery card for sellers | 6
7 | Tour Guide | Create/ Read/ Update my profile with my information as a tour guide including mobile number, years of experience, previous work(if exists), etc.. if accepted as a tour guide on the system | 1 | Similar to LinkedIn individual profiles | 6
8 | Advertiser | Create/ Read/ Update my profile with my information as a company including a link to my website, hotline, company profile, etc.. if accepted as an advertiser on the system | 1 | Similar to LinkedIn company profiles | 6
9 | Seller | Create/ Read/ Update my profile with my information as a Seller including name and description. if accepted as a seller on the system | 1 |  | 6
10 | Tour Guide/ Advertiser/ Seller | Upload picture | 1 | Photo for tour guide, logo for advertiser/seller | 3
11 | Tourist | Read/ Update my profile that includes all my information including my wallet | 1 | Username and wallet is not editable | 2
12 | Admin | View the documents uploaded by tour guides/ advertisers/ sellers that are trying to register on the system | 1 |  | 2
13 | Admin | Accept/ Reject tour guides and advertisers and sellers based on uploaded documents | 1 |  | 4
14 | Tour Guide/ Advertiser/ Seller | Accept the terms and conditions if accepted on the system | 1 | Cannot use the system until the terms and conditions are accepted | 3
15 | Tourist/ Tour Guide/ Advertiser/ Seller | Request my account to be deteled off the system | 1 | An account will be deleted only if no events or activities or itenararies are upcoming and have bookings that are paid for. The account profiles along with all associated events, activities and itineraries will not be visible to tourists. | 4
16 | Admin | Delete account off system | 1 |  | 2
17 | Admin | Add Tourism Governer to the system by creating a unique username and password | 1 |  | 2
18 | Admin | Add another admin to the system by creating a unique username and password | 1 |  | 2
19 | Advertiser | Create/ Read/ Update/ Delete an activity by entering its date, time, location (using Google Maps), price (or price range), category, tags, special discounts, if booking is open | 1 | The advertiser is a company or entity such as Ski Egypt, Kidzania, Helmyman Events, Tickets Marche, Taskarti, London cab, etc... | 8
20 | Tour Guide | Create/ Read/ Update/ Delete an itinerary along with the details including activities, locations to be visited, timeline, duration of each activity, language of tour, price of tour, available dates and times, accesibility, pick up/ drop off location. | 1 | An itinerary cannot be deleted if bookings are already made | 8
21 | Tourism Governor | Create/ Read/ Update/Delete museums and historical places along with it's details like description, pictures, location, opening hours, ticket prices | 1 | Tickets prices vary if foreigner, native or student | 8
22 | Tourism Governor | Create tags for different historical locations (e.g., type, historical period). | 1 | Types are: Monuments,Museums, Religious Sites,Palaces/Castles | 2
23 | Admin | Create/ Read/ Update/ Delete an activity category (food, stand up comedy, concert, party, bazaars. exhibitions, sports matches/ events, parks, etc..) for activities | 1 |  | 8
24 | Admin | Create/ Read/ Update/ Delete preference tags (historic areas, beaches, family-friendly, shopping, budget-friendly) | 1 |  | 8
25 | Tour Guide | Activate/ deactivate an itinerary with bookings | 1 | Itineraries with bookings can only be deactivated. People who already booked will attend normally. The itinerary will disappear for those who have not yet booked anything. | 2
26 | Tour Guide/ Advertiser/Tourism Governer | View a list of all my created activities/ itineraries / museums and historical places | 1 |  | 3
27 | Admin | View a sales report containing all my revenue from different events/ itineraries/ sales from the gift shop | 1 | App rate must be 10% of any event/ itinerary booked and paid for online | 2
28 | Tour Guide/ Advertiser/ Seller | View a sales report containing all my revenue | 1 |  | 6
29 | Tour Guide/ Advertiser | Filter sales report based on a activity/ itinerary/date/month | 1 |  | 4